## predictive_maintenance_gantt2
Task ID | Stage | Task Name | Start Date | End Date | Estimated Duration (days) | Responsible Person | Exact Duration (days)
1 | setup | Project Initiation | 2025-01-01 | 2025-01-05 | 5 | Project Manager | 8
2 | setup | Requirement Analysis | 2025-01-06 | 2025-01-15 | 10 | Business Analyst | 9
3 | data preparation | Data Collection | 2025-01-16 | 2025-02-05 | 21 | Data Engineer | 21
4 | data preparation | Data Preprocessing | 2025-02-06 | 2025-02-20 | 15 | Data Scientist | 20
5 | modeling | Model Selection | 2025-02-21 | 2025-03-10 | 20 | Data Scientist | 20
6 | modeling | Model Training & Evaluation | 2025-03-11 | 2025-04-05 | 26 | ML Engineer | 26
7 | testing | Integration with IoT Devices | 2025-04-06 | 2025-04-25 | 20 | IoT Engineer | 20
8 | testing | System Testing | 2025-06-26 | 2025-07-10 | 15 | QA Engineer | 15
9 | implementation | Deployment & Monitoring Setup | 2025-07-11 | 2025-07-30 | 20 | DevOps Engineer | 20
10 | implementation | User Training & Documentation | 2025-07-31 | 2025-08-10 | 10 | Training Team | 10
11 | finalization | Performance Review & Optimization | 2025-08-11 | 2025-08-25 | 15 | Data Scientist | 15
12 | finalization | Project Handover & Closure | 2025-08-26 | 2025-08-30 | 5 | Project Manager | 5